## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Naga Nikhith | 2025-10-02 | YOLO model not loading due to version mismatch | Sprint 1 | Naga Nikhith | Functional | Updated Ultralytics and Torch versions | 2025-10-03 | Closed | Model loaded successfully
2 | Naga Nikhith | 2025-10-05 | OCR failed to detect text on blurred Aadhaar image | Sprint 1 | Naga Nikhith | Accuracy | Applied image preprocessing filters | 2025-10-06 | Closed | OCR accuracy improved
3 | Naga Nikhith | 2025-10-09 | Aadhaar number extracted incorrectly (extra digits) | Sprint 2 | Naga Nikhith | Logical | Added regex validation | 2025-10-10 | Closed | Extraction fixed
4 | Naga Nikhith | 2025-10-12 | App crashes when uploading non-image files | Sprint 2 | Naga Nikhith | Functional | Added file format validation | 2025-10-13 | Closed | App stable
5 | Naga Nikhith | 2025-10-15 | Verhoeff checksum not applied correctly | Sprint 3 | Naga Nikhith | Logical | Fixed checksum logic | 2025-10-16 | Closed | Validation working fine
6 | Naga Nikhith | 2025-10-18 | Flask app slow response during OCR | Sprint 3 | Naga Nikhith | Performance | Optimized image reading and model call | 2025-10-19 | Closed | Speed improved
7 | Naga Nikhith | 2025-10-21 | Incorrect field mapping in YOLO output | Sprint 3 | Naga Nikhith | Functional | Corrected label-to-field mapping | 2025-10-22 | Closed | Extraction accurate
8 | Naga Nikhith | 2025-10-24 | Fraud detection not triggered for invalid Aadhaar | Sprint 4 | Naga Nikhith | Logical | Added checksum verification step | 2025-10-25 | Closed | Fraud detection fixed
9 | Naga Nikhith | 2025-10-26 | OCR misreads certain fonts | Sprint 4 | Naga Nikhith | Accuracy | Trained model with new font samples | 2025-10-27 | Closed | Accuracy improved
10 | Naga Nikhith | 2025-10-28 | Minor UI issues in Flask web interface | Sprint 4 | Naga Nikhith | UI/UX | Adjusted layout and added alerts | 2025-10-28 | Closed | Final UI clean and responsive

## Sheet2
Logical
User Interface
Maintainability
Standards
Others